## Sheet1
2015 Conservation Commission Priority Projects 10-13-2015 update
| Project Name | Description | Est Cost | Status | Scheduled completion
Top priorities
1 | Canterbury Trail (Greenbelt Plan # 3 and 4) | Install Potential trail #4 on existing easement to connect to new trails in Cottage Brook; work with Canterbury on the Cape Association on Potential trail #3, east of #4. |  | Canterbury Association President Fred Sprague to attend 10-13-2015 CC mtg
2 | Loveitt Woods access | Obtain public access rights to Loveitt Woods, with a focus on the existing access off Glenden Rd or Rock Wall Ln/Oakhurst Rd, and from Shore Rd (Potential trail #5). |  | Inquiries have been made to property owners. One owner has offered an easement.
3 | Alewives Brook to the Sea Trail (Greenbelt Plan #18) | Obtain public access rights for Potential trail #18 along Alewives Brook and install trail. |  | On hold at this time.
4 | Dyer Woods to Oakhurst Trail (Greenbelt Plan #1) | Obtain public access rights for Potential trail #1 connecting Dyer Woods to Oakhurst Rd/Loveitt Woods. |  | Planner to prepare map and analysis of trail area
5 | Sawyer Marsh/Trout Brook trail (Greenbelt Plan #2) | Obtain public access rights and construct, in partnership with the City of South Portland, Potential trail #2 |  | Planner to investigate obtaining public access rights
Medium priorities
6 | Gull Crest Outer Loop Trail | Add third board to existing 2-board walkway and extend existing boardwalk 3-boards wide about 400' | $2600, committed by CC | Project is programmed for construction by the Boy Scouts Camperee and Eagle Scout candidate Peter DiNinno | Fall 2015
6b | Gull Crest Outer Loop Trail Part 2 | On remainder of long stretch, add 3rd board to existing boardwalk | 5000 | Determine length, estimate cost
7 | Nordic Trail surface rehab | Minor improvements to trail surface located at Gull Crest to maintain trail integrity and drainage |  | Public Works reset culverts fall 2014. Identify other needs and coordinate with PW
Other projects
8 | Pollack Brook bridge and adjacent trail/cemetary (Greenbelt Plan #13) | There is an existing trail with a failed bridge (51' long) across the brook, and an existing trail adjacent to an undocumented cemetery |  | Commission to discuss next steps following site visit 9-15-2015
9 | Riverside Cemetary to the Spurwink Marsh (Greenbelt Plan #13 partial) | This project would establish/re-establish a connection from the Spurwink Marsh, across from the Scarborough access to the Riverside Cemetary, potentially to the existing road system. |  | Combined with #8.
10 | Winnick Woods blue trail boardwalk | A section of the blue trail needs bridging over a muddy section | $1,500 estimate | On hold as a good eagle scout project
11 | Encroachment aerial assessment | Using new 2015 aerial photos, review all town open space boundary lines for possible encroachments by abutters, notify abutters that encroachments should be avoided | 0 | On hold waiting for delivery of new aerials. | Winter/ Spring 2016
12 | Enhanced trail buffering | Assess greenbelt trails for locations where additional buffering from adjacent properties may be appropriate |  | Potentially combined with Project 11 above. May also be eagle scout candidate project.
13 | Cross Town Trail Signage | Install 2.0" metal disc along length of Cross Town Trail. | 750 | Signage ordered. | Fall 2015 /Winter 2016
Other Projects
?