## Sheet1
2015 Conservation Commission Priority Projects 12-4-2015 update
| Project Name | Description | Est Cost | Status | Scheduled completion
Top priorities
1 | Canterbury Trail (Greenbelt Plan # 3 and 4) | Install Potential trail #4 on existing easement to connect to new trails in Cottage Brook; work with Canterbury on the Cape Association on Potential trail #3, east of #4. |  | Met with Canterbury on the Cape Association and they are ok to proceed to site walk. Spoke with R. Preston, also ok to proceed to site walk. Talking with Bothel, not ready for site walk yet.
2 | Loveitt Woods access | Obtain public access rights to Loveitt Woods, with a focus on the existing access off Glenden Rd or Rock Wall Ln/Oakhurst Rd, and from Shore Rd (Potential trail #5). |  | Van Dessels support status quo, no easement at this time. No additional contact with other property owner this year. ON HOLD
3 | Alewives Brook to the Sea Trail (Greenbelt Plan #18) | Obtain public access rights for Potential trail #18 along Alewives Brook and install trail. |  | Planner has discussed possible easement with current property owner, as part of 3-lot subdivision. Site walk with PB scheduled for 12-6-2015.
4 | Dyer Woods to Oakhurst Trail (Greenbelt Plan #1) | Obtain public access rights for Potential trail #1 connecting Dyer Woods to Oakhurst Rd/Loveitt Woods. |  | Planner to prepare map and analysis of trail area
5 | Sawyer Marsh/Trout Brook trail (Greenbelt Plan #2) | Obtain public access rights and construct, in partnership with the City of South Portland, Potential trail #2 |  | Planner to investigate obtaining public access rights
Medium priorities
6 | Gull Crest Outer Loop Trail | Add third board to existing 2-board walkway and extend existing boardwalk 3-boards wide about 400' | $2600, committed by CC | Project complete.
6b | Gull Crest Outer Loop Trail Part 2 | On remainder of long stretch, add 3rd board to existing boardwalk | 5000 | Boy Scout project complete. Scheduling meeting with contractor to identify final extensions needed and obtain cost estimate
7 | Nordic Trail surface rehab | Minor improvements to trail surface located at Gull Crest to maintain trail integrity and drainage |  | Public Works reset culverts fall 2014. Identify other needs and coordinate with PW. Planner to pursue surface improvements.
Other projects
8 | Pollack Brook bridge and adjacent trail/cemetary (Greenbelt Plan #13) | There is an existing trail with a failed bridge (51' long) across the brook, and an existing trail adjacent to an undocumented cemetery |  | Retained Sebago Technics to do feasibility/permitting study. Contract signed, work underway.
9 | Riverside Cemetary to the Spurwink Marsh (Greenbelt Plan #13 partial) | This project would establish/re-establish a connection from the Spurwink Marsh, across from the Scarborough access to the Riverside Cemetary, potentially to the existing road system. |  | Combined with #8.
10 | Winnick Woods blue trail boardwalk | A section of the blue trail needs bridging over a muddy section | $1,500 estimate | On hold as a good eagle scout project
11 | Encroachment aerial assessment | Using new 2015 aerial photos, review all town open space boundary lines for possible encroachments by abutters, notify abutters that encroachments should be avoided | 0 | On hold waiting for delivery of new aerials. | Winter/ Spring 2016
12 | Enhanced trail buffering | Assess greenbelt trails for locations where additional buffering from adjacent properties may be appropriate |  | Potentially combined with Project 11 above. May also be eagle scout candidate project.
13 | Cross Town Trail Signage | Install 2.0" metal disc along length of Cross Town Trail. | 750 | Signage arrived. Need to arrange installation. Road stencils for Spring 2016. | Fall 2015 /Winter 2016