## Sheet1
Children's Garden Construction Plan | Work Done By: | Schedule
Phase 1: Site Preparations
Remove invasive Black Swallowwort | Volunteer Labor | Late 2013, ongoing
Remove Trees & Pruning | Volunteer Labor, Town | Fall 2013,Winter/Spring 2014
Phase 1: Contracted Work |  | Spring/ Summer 2015
Demolition | Skip Murray
Clearing & Grubbing
Preliminary Grading
Install Stone Dust Paths
Install Large Boulder Walls
Meadow Tunnel Installation
Phase 2: Contracted Work |  | Summer/Fall 2015
Stone Circle Repair | Bidder
Stair installation
Plant Bed Preparations
Stone Walls
Paving/surfacing
Tunnel Installation
Irrigation
Stream & Biofilter Installation | Robins Nest Aquatics | Summer/ Fall 2015
Tree Fort Construction | Andy Buck | Summer/ Fall 2015
Stone Circle Timberframe Canopy | Andy Buck | Summer/ Fall 2015
Phase 3: Planting
Plant installation | Bidder | Fall 2015
Meadow Installation | Bidder | Fall 2015/Spring 2016
Play Areas
Loose Parts Maintenance |  |  | ½ day / week
Add / remove play elements |  |  | 5 years
Replace Stumps | Town or maintenance crew |  | 3-5 years