## A
360.20.41 Charles Road Sewer Rehabilitation |  |  |  | Date: January 28, 2013
AMEC ENVIRONMENT & INFRASTRUTURE, INC. |  | ENGINEER'S PROGRESS ESTIMATE
SEWER REHABILITATION - CHARLES ROAD
NOTES:
1) QUANTITIES ARE BASED UPON CHARLES ROAD PLANS PREPARED BY AMEC & ISSUED FOR BID 1-28-13.
2) UNIT PRICES ARE BASED UPON AMEC'S REVIEW OF RECENT BIDS RECEIVED BY TOWN OF CAPE ELIZABETH,
MDOT, AND CITY OF PORTLAND.
3)
AMEC HAS ASSUMED, FOR PURPOSES OF THIS ESTIMATE, THAT TRENCH ROCK WILL BE ENCOUNTERED
FROM APPROXIMATELY THE INVERTS OF EXISTING PIPES TO 6-INCHES
BELOW PROPOSED PIPE INVERTS. ALSO, ONLY 10 CY OF MASS ROCK IS INCLUDED HERE-IN AS A TOKEN AMOUNT.
4) ROCK QUANTITIES SHOULD BE UPDATED BASED UPON PROBING RESULTS.
5) BID ITEMS & QUANTITIES SHOULD BE UPDATED PRIOR TO ADVERTISING FOR BIDS.
Updated Engineer's Estimate 1-28 2013
Unit
Item No. | Description | Unit | Qty |  |  | Price | Amount
1 | Test Pits | CY | 15 |  |  | 80 | 1200
2 | Unsuitable Material Excavation Below Grade | CY | 20 |  |  | 30 | 600
3 | Trench Rock | CY | 135 |  |  | 200 | 27000
4 | Mass Rock Excavation | CY | 10 |  |  | 150 | 1500
5 | Common Excavation | CY | 1976 |  |  | 11 | 21736
6 | Remove Existing Manholes or Catch Basins | EA | 3 |  |  | 500 | 1500
7 | Remove and Plug Existing Pipes | LF | 80 |  |  | 30 | 2400
8 | Furnishing Off-Site Select Backfill Material | CY | 20 |  |  | 25 | 500
9 | Stone Pipe Bedding | CY | 10 |  |  | 30 | 300
10 | Sand Pipe Bedding | CY | 10 |  |  | 25 | 250
11 | Common Borrow | CY | 35 |  |  | 9 | 315
12 | Aggregate Base Gravel | CY | 225 |  |  | 30 | 6750
13 | Aggregate Subbase Gravel | CY | 1110 |  |  | 25 | 27750
14 | 6-inch HDPE Storm Drain (Foundation Laterals) | LF | 50 |  |  | 45 | 2250
15 | 12-inch HDPE Storm Drain | LF | 100 |  |  | 55 | 5500
16 | 12-inch HDPE Under Drain (Type C) | LF | 350 |  |  | 65 | 22750
17 | 6-inch HDPE Under Drain (Type B) | LF | 100 |  |  | 35 | 3500
18 | HDPE Insert-A-Tee | EA | 2 |  |  | 200 | 400
19 | 4-foot Diameter Catch Basin | EA | 7 |  |  | 3000 | 21000
20 | 4-foot Diameter Drainage Manhole | EA | 2 |  |  | 3000 | 6000
21 | 6-inch Sanitary Sewer Services | LF | 400 |  |  | 60 | 24000
22 | 8-inch Sanitary Sewer | LF | 596 |  |  | 70 | 41720
23 | 1.5-inch Force Main | LF | 144 |  |  | 70 | 10080
24 | Sanitary Service Connection | EA | 18 |  |  | 200 | 3600
25 | 2-inch Foam Board Insulation | SF | 660 |  |  | 3 | 1980
26 | 4-foot Diameter Sanitary Sewer Manhole | EA | 3 |  |  | 4000 | 12000
27 | Alter Existing Drop Manhole | EA | 1 |  |  | 4000 | 4000
28 | Hot Bit. Base Pavement (MDOT SuperPave 19 mm) | TON | 305 |  |  | 100 | 30500
29 | Hot Bit. Surface Pavement (MDOT SuperPave 9.5 mm) | TON | 205 |  |  | 105 | 21525
30 | Hot Bituminous Driveways | SY | 195 |  |  | 60 | 11700
31 | Permanent Hot Bituminous Trench Patch | TON | 10 |  |  | 150 | 1500
32 | Temporary Cold Bituminous Trench Patch | TON | 10 |  |  | 150 | 1500
33 | Bituminous Cape Cod Berm Curb | LF | 765 |  |  | 7 | 5355
34 | Concrete Sidewalk/ Concrete Driveway (House #4) | SY | 295 |  |  | 95 | 28025
35 | Loam and Seed | SF | 7500 |  |  | 0.6 | 4500
36 | Calcium Chloride | TON | 2 |  |  | 600 | 1200
37 | Construction Signage and Traffic Control Devices | LS | 1 |  |  | 5000 | 5000
38 | Flaggers | LS | 1 |  |  | 20000 | 20000
39 | Erosion Control | LS | 1 |  |  | 10000 | 10000
40 | Hand Labor, Straight Time | HR | 8 |  |  | 35 | 280
41 | Foreman, Straight Time | HR | 8 |  |  | 50 | 400
42 | All Purpose Excavator | HR | 8 |  |  | 120 | 960
43 | Heavy-Duty Purpose Excavator | HR | 8 |  |  | 150 | 1200
44 | Front End Loader | HR | 8 |  |  | 95 | 760
45 | Grader | HR | 8 |  |  | 150 | 1200
46 | Truck, Small | HR | 8 |  |  | 55 | 440
47 | Truck, Large | HR | 8 |  |  | 70 | 560
48 | Mobilization | LS | 1 |  |  | 20000 | 20000
49 | Concrete Brick Driveway Reconstruction | SY | 13 |  |  | 150 | 1950
50 | Curb Ramp Detectable Warning Field | SF | 6 |  |  | 80 | 480
| Enginnering, Construction Admnin etc. |  | 1 |  |  | 36000 | 36000
|  |  | TOTAL |  | 0 |  | 455616
|  |  | 10% Contingency |  |  |  | 42000
|  |  | TOTAL |  |  |  | 497616