## Sheet1
Total Projected Construction Cost | 3404000 | Pre-Bid Costs | Paid Through June 11 2014 | Invoiced | Total
Total Projected Project Cost | 4000000
A/E fee for Renovation | $942,000 @ 12.5%=$117,500* .75 | 88125
A/E fee for New Construction | $2,462,000 @ 9.0%=$221,580* .75 | 166185 | 85788 | 37829.68 | 123617.68
Planning Board Review |  | 25000 |  |  | 0
Construction Manager-Pre Bid |  | 10000 |  |  | 0
Land Survey and Geotechnical |  | 5000 | 5073 |  | 5073
Hazardous Materials Survey |  | 5000 |  |  | 0
State Fire Marshal Review Fees |  | 1500 |  |  | 0
Owner’s Contingency |  | 15000 |  |  | 0
Legal and Bond Issuance fees |  | 25000 | 38.1 |  | 38.1
Total Pre-Bid/Pre Bond Issuance Expense |  | 340810 | 90899.1 | 37829.68 | 128728.78
Planniing Board Review Costs
Included in Above Line