Cape Elizabeth Town Manager Search

Draft Timeline

September-2016

September 21 Wednesday

- Meeting(s) with Town Council to discuss and finalize process for Town Manager search.

September 27 Tuesday

- Meetings with staff on characteristics they would like in a new Town Manager.

October 19 Wednesday

- Public meeting to hear from citizens on what characteristics they would like in a new Town Manager.

October 25 Tuesday

- Council meets to hear results of staff, public and Council comments concerning new manager and approves ad.

October 26 Wednesday

- Begin advertising for Town Manager position (3 ½ weeks)

November 18 Friday

- Deadline for applications

November-23 Wednesday

- Notebooks delivered to Council

November 29 Tuesday (date flexible)

- Council  meets to review candidates resumes and decides on which candidates to interview

December 12-15 Monday to Thursday

- First round of interviews. Most likely 2 days. Council then decides on which candidates to select for a second round. Complete background checks on finalists initiated by EPCG.

January 3-5 Tuesday to Thursday

- Second round of interviews for (2) finalists. Most likely 2 separate days.  Department Heads meet with candidates and community gathering for citizens to meet Candidates. Council has second interviews with both candidates. Council selects a finalist.

January 6-13

- Contract negotiations with finalist.

January 17 Tuesday

- Council votes and announces starting date of new Manager